## Possible taskstreams
Sub-Committee* | Activity | Target Date | Possible Deliverables
Pensions | Prepare for role actuaries can play in risk management under IORP II | Spring 2018 | Prepare short note summarising current IORP II implementation state of play in relation to risk management.
Pensions | Paper on actuarial involvement in IORP risk management | Autumn 2018? | Prepare note setting out views on how best to do risk management under IORP II and how actuaries can assist. Note to cover how actuaries working in actuarial function (AF) may assist, how other actuaries outside the AF function (e.g. in the risk function) may assist and whether / how the two can / should overlap
CRO / RHF | European RMF and CRO forum | Summer 2019 | Plan and implement an initial face-to-face forum targeting European RMFs and CRO, providing regular updates to the RMC in the meantime
Insurance | ORSA standards and guidance | Autumn 2018 | Provide someone who will act as liaison between RMC and AAE's existing ORSA standards task force (which reports to the Insurance Committee)
Insurance | ORSA support material | Spring 2019 | Develop material that explores how to add value through ORSA (i.e. not targeting standards as such)
Whole RMC | Paper on promotion of actuary in risk management | Spring 2018 | Refresh and update previously prepared paper
Whole RMC | Risk Management Article Database | Spring 2018 | Present proposal to RMC on whether / how to facilitate creation and population of such a database
Insurance | AAE RM response to LTG Review, UFR and EIOPA 2nd Set of Advice on Solvency II etc. | Spring 2018 | In March 2018 propose response, if called for, to EIOPA proposals on these topics
Insurance | Modelling of low / negative interest rates | Spring 2018 | Identify whether need to respond to EIOPA on interest rate modelling
Whole RMC (but with Insurance bias?) | Modelling of low / negative interest rates | Autumn 2018? | Proposed refined ways of modelling interest rates in a low / negative interest rate environment
Insurance | IFRS 17 | Spring 2018 | Prepare brief note for RMC summarising: (a) IFRS 17 and what we think the IAA has done or is planning to do in relation to IFRS 17 (b) What aspects of IFRS 17 are specifically risk management related (c) Which elements of (b) are specifically European-related and therefore likely to be within the scope of AAE RMC
Insurance | ICS | Autumn 2018 | Prepare note for RMC summarising: (a) Proposed group-wide global Insurance Capital Standard (ICS) and what we think the IAA has done or is planning to do in relation to them (and related material such as COMFRAME) (b) What aspects of ICS and related material are specifically risk management related (c) Which elements of (b) are specifically European-related and therefore likely to be within the scope of AAE RMC
Insurance | Duration Management of insurance contracts | Autumn 2018 | Develop paper on management of duration of contracts, including impact on various elements of Solvency II balance sheet and SCR
Insurance? | Promoting consistent approaches amongst European RM Actuaries | TBD | TBD
Insurance | Interaction between sharp rises in interest rates and lapse behaviour | Spring 2018 | Report to RMC on progress reviewing this topic
Whole RMC | Reach out to other European risk management organisations | Spring 2019 | Identify targets to contact and initiate contact
Wider Fields / Investment | Remuneration policy | Autumn 2018 | Prepare paper explaining how remuneration policy interacts with risk management (not limited to financial sector) and actuarial perspectives
Insurance | Internal model comparability | Autumn 2018 | Scope out what is practical to deliver
Wider Fields / Investment | Sovereign risk | Autumn 2018 or Spring 2019 | Prepare paper suitable for presenting to ECA on relevance of sovereign risk to actuaries and how to manage it
Wider Fields / Investment | Rewarded versus unrewarded risk | Spring 2019 | Prepare paper on risk management and upside risk capture
Wider Fields / Investment | Liquidity risk | Spring 2019 | Compare and contrast different perspectives on liquidity between different EU institution types that actuaries advise and different approaches to liquidity risk management
Whole RMC | Model risk | Summer 2019 | Prepare paper on model risk
Whole RMC | Operational Risk | Autumn 2018 | Prepare proposal for how RMC might expand its coverage of operational risk, expanding on earlier draft, and identify scope to present at suitable venue
* Projects have been categorised into:
Whole RMC | I.e. span all elements of RMC
Subcommittees:
Pensions | Pension specific
Insurance | Insurance specific
Wider Fields / Investment | Risk management that is largely neither pension nor insurance specific