## Possible taskstreams
AAE Risk Management Committee - Project / Taskstream List as at 16 May 2018
Sub-Committee* | Activity | Target Date | Possible Deliverables | Other Comments
Pensions | Prepare for role actuaries can play in risk management under IORP II | Spring 2018 | Prepare short note summarising current IORP II implementation state of play in relation to risk management. | Write in conjunction with similar exercise but with broader scope already being undertaken by the AAE Pensions Committee? Deferred from Spring 2018 to Autumn 2018
Pensions | Paper on actuarial involvement in IORP risk management | Autumn 2018 | Prepare note setting out views on how best to do risk management under IORP II and how actuaries can assist. Note to cover how actuaries working in actuarial function (AF) may assist, how other actuaries outside the AF function (e.g. in the risk function) may assist and whether / how the two can / should overlap | If possible, get AAE Secretariat or Pension Committee to advise on likely EIOPA timing of issuing guidance. EIOPA seem to be interested in proportionate sharing of control functions in insurance, so presumably will also be interested in this for pensions
CRO / RFH | European RMF and CRO forum | Summer 2019 | Plan and implement an initial face-to-face forum targeting European RMFs and CRO, providing regular updates to the RMC in the meantime | Could perhaps happen alongside the planned European Congress of Actuaries in June 2019. If so, liaise with Ad Kok and others involved with ECA. Current thinking is now to have an initial meeting in Q3 or Q4 2018
Insurance | ORSA standards and guidance | Autumn 2018 | Provide someone who will act as liaison between RMC and AAE's existing ORSA standards task force (which reports to the Insurance Committee) | Provide updates to RMC meetings in the meantime
Insurance | ORSA support material | Spring 2019 | Develop material that explores how to add value through ORSA (i.e. not targeting standards as such) | Corresponding IAA work may provide a template, if specific European dimension can be identified
Whole RMC | Paper on promotion of actuary in risk management | Autumn 2018 | Refresh and update previously prepared paper | Paper presented to RMC in Spring 2018. To be refined bearing in mind feedback and target audience for Autumn 2018
Whole RMC | Risk Management Article Database | Autumn 2018 | Present proposal to RMC on whether / how to facilitate creation and population of such a database | Could just involve a proposal to link to corresponding databases of individual member associations and AFIR? Would then require interaction with Ad Kok to organise such links
Insurance | AAE RMC response to LTG Review, UFR and EIOPA 2nd Set of Advice on Solvency II etc. | Spring 2018 | In March 2018 propose response, if called for, to EIOPA proposals on these topics | Should be done in liaison with existing AAE Solvency II Project Task Force. Done
Insurance | AAE RMC response to LTG Review etc. | Ongoing | Assist Solvency II Working Group | Likely significant amount of activity over coming months, timeline TBA
Insurance | Modelling of low / negative interest rates | Spring 2018 | Identify whether need to respond to EIOPA on interest rate modelling | Earlier suggestions provided to EIOPA focusing on use of shifted lognormal did not work well in EIOPA back-tests, so EIOPA asked AAE in December for further suggestions. MK included some wording in AAE response to 2nd Set of Advice. Done - now merged with broader input into LTG review etc.
Whole RMC (but with Insurance bias?) | Modelling of low / negative interest rates | Autumn 2018? | Proposed refined ways of modelling interest rates in a low / negative interest rate environment | May need to be sooner, to align with EIOPA expectations, see above
Insurance | IFRS 17 | Spring 2018 | Prepare brief note for RMC summarising: (a) IFRS 17 and what we think the IAA has done or is planning to do in relation to IFRS 17 (b) What aspects of IFRS 17 are specifically risk management related (c) Which elements of (b) are specifically European-related and therefore likely to be within the scope of AAE RMC | Should be prepared in liaison with the AAE’s newly formed IFRS 17 task force. Aspects that might be specifically RM orientated could include e.g. if firms are expected to start to manage their business by reference to IFRS 17 or because firms might need because of coincident introduction of IFRS 9 to enhance their credit risk models. Paper provided but topic carried forward as Daphné ill Spring 2018 RMC meeting
Insurance | ICS | Autumn 2018 | Prepare note for RMC summarising: (a) Proposed group-wide global Insurance Capital Standard (ICS) and what we think the IAA has done or is planning to do in relation to them (and related material such as COMFRAME) (b) What aspects of ICS and related material are specifically risk management related (c) Which elements of (b) are specifically European-related and therefore likely to be within the scope of AAE RMC | Malcolm to share with taskstream members experience of debates on this at IAA EFRC and IAA Insurance Regulation Committee
Insurance | Duration Management of insurance contracts | Autumn 2018 | Develop paper on management of duration of contracts, including impact on various elements of Solvency II balance sheet and SCR | Impact section might be influenced by outcome of EIOPA Second Set of Advice. Paper provided for Spring 2018 RMC but still to be finalised
Whole RMC | Promoting consistent approaches amongst European RM Actuaries | Spring 2019 | Initial proposal was to promote consistent approaches about risk management system such as: (a) How we understand RM should be effectively implemented in insurance sector? And what doe we mean by effectiveness of ERM (b) Do we understand in the same way RM elements, vocabulary, RM goals, principles etc. (c) How to organise RM process to make it most efficient and valuable to the organisation (d) What is ERM maturity and how to evaluate it etc. | Suggest also include internal model comparability within this workstream. If so, it may then be worth referring to banking experience where comparability of IRB models was not as good as had been hoped. Malcolm to speak to Tony O'Riordan (chair AAE Insurance Committee) to check IC interest / activity in this space.
Insurance | Interaction between sharp rises in interest rates and lapse behaviour | Autumn 2018 | Report to RMC on progress reviewing this topic | Insurance Committee also looking at this topic
Whole RMC | Reach out to other European risk management organisations | Spring 2019 | Identify targets to contact and initiate contact | AAE Secretariat may be able to assist with names / contacts
Wider Fields / Investment | Remuneration policy | Autumn 2018 | Prepare paper explaining how remuneration policy interacts with risk management (not limited to financial sector) and actuarial perspectives | Would need to identify European dimension?
Wider Fields / Investment | Sovereign risk | Autumn 2018 or Spring 2019 | Prepare paper suitable for presenting to ECA on relevance of sovereign risk to actuaries and how to manage it. Eduardo to collate material supplied by Christoph to see if sufficient new insights available to make this topic worth pursuing | Would need to decide whether focus should just be on sovereign debt or on relationships with sovereigns more generally
Wider Fields / Investment | Rewarded versus unrewarded risk | Spring 2019 | Prepare paper on risk management and upside risk capture | May focus on investment risk where these concepts are better established, but ideally would also bring in analogies applicable to other RM areas. Again ECA might provide a suitable broader forum at which to present such a paper
Wider Fields / Investment | Liquidity risk | Spring 2019 | Compare and contrast different perspectives on liquidity between different EU institution types that actuaries advise and different approaches to liquidity risk management | E.g. analyse robustness of MA and VA under Solvency II and whether equivalents are appropriate for other EU investor types? Could also refer to EU Capital Market and Sustainability agendas
Whole RMC | Model risk | Summer 2019 | Prepare paper on model risk | Some papers have been prepared by working parties in individual member associations, e.g. IFoA. Can they be leveraged and is there a European angle?
Whole RMC | Operational Risk | Autumn 2018 | Prepare proposal for how RMC might expand its coverage of operational risk, expanding on earlier draft, and identify scope to present at suitable venue | Would ECA be a suitable target venue?
Whole RMC | Reputational and Conduct Risk | Autumn 2019 | Exact deliverable still to be scoped | Would ECA be a suitable target venue?
Wider Fields / Investment | PEPPs | TBA | Contribute to AAE's response on PEPPs | Unclear how best to coordinate RMC input with Pension Committee input, as neither appears keen to take a lead. Also, AAE has already issued a discussion paper on this topic
Whole RMC? | Calibration of ESGs | TBA | Exact deliverable still to be scoped | Anina would like someone else involved too
* Projects have been categorised into:
Whole RMC |  | I.e. span all elements of RMC
Sections:
Pensions |  | Pension section
Insurance |  | Insurance section
Wider Fields / Investment |  | Topics largely neither pension nor insurance specific
CRO / RFH |  | Chief Risk Officer / Risk Function Holder community stream